## Slide 1
Enterprise Workforce Management Platform
Phase 1 Proposal: In-House Scheduling Engine, SDLC Blueprint, Required Timeline & Stakeholder Expectations

## Slide 2
Strategic Context & Business Case
Transitioning from manual, spreadsheet-driven operations to a centralized enterprise scheduling engine.

## Slide 3
Current Operational Challenges
Spreadsheet Reliance: Decentralized Excel planning causes scheduling conflicts and manual calculation errors across sites.
High Recurring Cost: Expensive per-seat vendor license fees for legacy third-party tools like NICE & Verint.
Data Fragmentation: Lack of a single source of truth for rosters, skills, and leave tracking.
Strategic In-House Solution
Centralized WFM Platform: Unified system for roster creation, shift planning, and real-time coverage tracking.
Zero Seat Licensing: Fully owned software IP with zero recurring per-agent vendor subscription costs.
AI-Ready Foundation: Clean structured data architecture prepared for Phase 2 automated ML forecasting.
Business Opportunity

## Slide 4
Operational Speed & Efficiency
Compress roster creation timelines from multiple days down to hours. Planners receive dynamic templates, automated validation, and instant publish capabilities.
Cost & Governance Control
Eliminate external software licenses while providing full audit trails, role-based access control, and centralized coverage tracking across all operational units.
90%
Reduction in manual spreadsheet scheduling overhead
100%
Owned IP platform with zero third-party per-agent seat fees
Core Objectives & Value Drivers

## Slide 5
SDLC Architecture & Tech Stack
End-to-End Software Development Life Cycle methodology, stack, and functional modules.

## Slide 6
1. Requirements & Discovery
Eliciting business rules, shift structures, leave policies, and site hierarchies. Creating Business Requirement Documents (BRD) & Functional Specs.
2. System Architecture
Designing database schemas in SQL Server, UI/UX wireframes/prototypes for scheduling canvas, and defining RBAC security controls.
3. Iterative Engineering
Sprint-based engineering in .NET MVC (C#) & HTML5/jQuery UI. Building user roles, roster master, capacity planner, and rule engines.
4. Testing & Quality Assurance
Unit testing, system integration testing (SIT), security VPTA vulnerability audits, load testing, and formal User Acceptance Testing (UAT).
5. Deployment & Cutover
Production environment provisioning on IIS, database migration, CI/CD automated release cutover, and planner end-user onboarding.
6. Maintenance & Hypercare
Post-launch 30-day hypercare support, performance monitoring, bug fixes, and transitioning platform baseline to Phase 2 AI/ML roadmap.
Software Development Life Cycle (SDLC)

## Slide 7
1. User & Org Setup
Role-based access (RBAC), domain single sign-on (SSO), hierarchical modeling for LOBs, operational sites, skill matrix, and site calendars.
2. Roster & Capacity Engine
Employee master import, skill tagging, leave approvals, capacity planning workspace, FTE requirement modeling, and shift assignment templates.
3. Builder UI & Analytics
Interactive drag-and-drop schedule builder, version locking/history, real-time staffing coverage, agent utilization, and system audit logging.
Phase 1 Functional Modules

## Slide 8
Architecture Layer | Selected Technology | Technical Rationale & Capability
Application Core | .NET MVC Framework (C#) | High-performance enterprise backend with robust MVC architecture and security controls.
User Interface | Custom UX / jQuery / HTML5 | Fast, responsive interactive scheduling canvas with minimal footprint and high client compatibility.
Database Engine | Microsoft SQL Server | Relational data integrity, high-throughput transactional processing, and enterprise audit capabilities.
Web Hosting | Internet Information Services (IIS) | Hardened Windows Server hosting with Windows Authentication integration and SSL termination.
DevOps & Source | Azure DevOps / Git | Automated CI/CD release pipelines, backlog management, and secure central code repository.
Technology Stack Blueprint

## Slide 9
Required Timeline & Expectations
Detailed schedule duration, milestone gates, resource commitments, and stakeholder success criteria.

## Slide 10
Month 1
Requirements & Architecture: BRD creation, DB schema, UI/UX prototypes & CI/CD setup.
Gate 1: Specs Sign-off
Months 2–7
Sprint Engineering: 12 bi-weekly sprints building Org Hierarchy, Roster Master & Builder UI.
Gate 2: Code Freeze
Months 8–9
QA, Security & Cutover: SIT execution, VPTA penetration test, business UAT & IIS go-live.
Gate 3: Production Go-Live
Post Launch
Hypercare & Handoff: 30-day post go-live operational support, team training & AI roadmap.
Gate 4: Operational Sign-off
Required Timeline & Critical Milestones

## Slide 11
From Executive Leadership
From WFM Operations SMEs
From IT & Infrastructure
Budget sign-off for Phase 1 execution (₹1.50–2.50 Cr).
Sponsorship for organizational change management.
Approval of dedicated project steering committee.
10–12 hrs/week time commitment in Month 1 for BRD rules.
Bi-weekly sprint review attendance & feedback.
Full-time involvement during Month 8 UAT execution.
SQL Server & Windows IIS VM provisioning in Month 1.
Domain Active Directory (SSO) integration support.
Security architecture & VPTA audit clearing.
Stakeholder Expectations & Commitments

## Slide 12
Operational Efficiency
Expectation: Roster creation time reduced from 3 days to under 4 hours per planning cycle.
Metric: 90% savings in planner labor hours across operational units.
Data & Compliance Quality
Expectation: 100% elimination of spreadsheet formula errors and unauthorized schedule overrides.
Metric: Complete audit trails and zero compliance non-conformances.
Financial Return (ROI)
Expectation: Total elimination of 3rd-party per-seat vendor licensing subscriptions.
Metric: Full capital cost payback expected within 14 months of go-live.
Project Success Criteria & Expectations

## Slide 13
Phase 1 Investment Breakdown

## Slide 14
Dedicated Cross-Functional SDLC Team (15 Headcount): 1 Project Manager, 1 Product Owner, 1 Solution Architect, 1 Tech Lead, 4 .NET Developers, 2 Frontend Developers, 2 QA Engineers, 1 DevOps Engineer, 1 UI/UX Designer.
Requirements & Testing SMEs: Dedicated WFM Operations SMEs for business rules elicitation & UAT validation; HR/Operations leads for site hierarchy alignment.
IT & Security Governance: DBA support for SQL Server provisioning, Infrastructure team for IIS deployment, and Security Team for VPTA audit.
Team Structure & Governance Model

## Slide 15
Executive Decision Needed
Approval requested for Phase 1 budget (₹1.50–2.50 Cr), required 9-month schedule, team allocation, and stakeholder commitments.